| BRANDING SCOPE OF WORK Brightline Studio LLC 214 Market Street, Suite 5, Austin, TX 78701, USA hello@brightline.example · +1 (512) 555-0142 Sample scope of work · dates in MM/DD/YYYY | SOW No.: SOW-2026-021 Date: 10/20/2026 Start date: 11/02/2026 |
| --- | --- |

| AGENCY Brightline Studio LLC Maya Torres, Managing Director hello@brightline.example Austin, TX, USA | CLIENT Kavya Home Decor Kavya Rao, Founder 88 Park Avenue, Pune, India kavya@kavyahome.example |
| --- | --- |

This scope of work covers a new brand identity for Kavya Home Decor, a handmade home decor brand moving from Instagram sales to its own online store.

# 1. Objectives

•  A distinctive brand identity that works on packaging, the website and social media.

•  A logo that reads clearly at 32 px on mobile and on a 1 m shop sign.

•  Brand guidelines the client's team can use without the agency.

# 2. Deliverables

| Deliverable | Qty | Format | Due |
| --- | --- | --- | --- |
| Brand discovery workshop and research summary | 1 | Workshop + PDF | Week 2 |
| Positioning statement and moodboards | 2 | PDF | Week 3 |
| Logo concepts | 3 | PDF presentation | Week 5 |
| Final logo suite (primary, stacked, icon) | 1 set | SVG, PNG, PDF | Week 6 |
| Color palette, typography and iconography | 1 system | PDF + font files | Week 7 |
| Brand guidelines | 24 pages | PDF | Week 8 |

# 3. Timeline

| Phase | Weeks | Milestone |
| --- | --- | --- |
| 1. Discovery and research | Weeks 1 to 2 | Research summary approved |
| 2. Strategy: positioning and moodboards | Week 3 | Direction approved |
| 3. Logo concepts and 2 revision rounds | Weeks 4 to 5 | Final logo approved |
| 4. Visual identity system | Weeks 6 to 7 (1.5 weeks) | Palette and type approved |
| 5. Brand guidelines and asset handover | Weeks 7 to 8 (1.5 weeks) | Files delivered |

# 4. Client Responsibilities

•  Join the 2-hour discovery workshop in week 1.

•  Name one decision maker who gives consolidated feedback.

•  Reply to each review within 3 business days. Later replies move the timeline by the same amount.

# 5. Revisions

The logo phase includes 2 revision rounds on one chosen concept. Other deliverables include 1 revision round. Further rounds are billed at USD 95 per hour.

# 6. Out of Scope

•  Website design or development

•  Printing and print management

•  Trademark search and filing

•  Photography and copywriting

# 7. Acceptance Criteria

Each deliverable is accepted when the client approves it in writing or does not request changes within 3 business days. The final logo files are accepted when they open correctly in the listed formats.

# 8. Fees and Payment Schedule

The total fee is USD 9,600, paid as follows:

| Payment | Due | Amount |
| --- | --- | --- |
| 1. On signing (40%) | 11/02/2026 | 3,840.00 |
| 2. On logo approval (30%) | End of week 5 | 2,880.00 |
| 3. On guidelines delivery (30%) | End of week 8 | 2,880.00 |

Total  USD 9,600.00

Invoices are due within 14 days. Ownership of the final logo and identity files passes to the client on full payment.

# 9. Change Requests

Any work outside this scope is requested in writing. The agency replies within 2 business days with the effect on fee and timeline, and the change starts only once both parties approve it in writing.

# Sign-Off

By signing below, both parties agree to this scope of work. It forms part of the service agreement between them.

| FOR THE AGENCY Name: ______________________________ Title: ______________________________ Signature: ______________________________ Date: ______________________________ | FOR THE CLIENT Name: ______________________________ Title: ______________________________ Signature: ______________________________ Date: ______________________________ |
| --- | --- |