| DIGITAL MARKETING SCOPE OF WORK Brightline Studio LLC 214 Market Street, Suite 5, Austin, TX 78701, USA hello@brightline.example · +1 (512) 555-0142 Sample scope of work · dates in MM/DD/YYYY | SOW No.: SOW-2026-024 Date: 10/20/2026 Start date: 11/02/2026 |
| --- | --- |

| AGENCY Brightline Studio LLC Maya Torres, Managing Director hello@brightline.example Austin, TX, USA | CLIENT GreenLeaf Organics Inc. Daniel Price, Head of Marketing 77 Cedar Lane, Portland, OR 97205, USA daniel@greenleaf.example |
| --- | --- |

This scope of work covers a 12-week digital marketing campaign to launch GreenLeaf Organics' new snack range online, across paid search, paid social, email and a campaign landing page.

# 1. Objectives

•  Drive online orders of the new range from launch week onward.

•  Grow the email list with a launch offer.

•  Report cost per order and return on ad spend each week.

•  KPIs are tracked and reported; no specific sales or ROAS figures are guaranteed.

# 2. Deliverables

| Deliverable | Qty | Format | Due |
| --- | --- | --- | --- |
| Campaign strategy, audiences and media plan | 1 | PDF + call | Week 2 |
| Campaign landing page | 1 | Live page | Week 4 |
| Paid search campaigns (setup and management) | 1 account | Google Ads | Weeks 4 to 12 |
| Paid social campaigns (setup and management) | 1 account | Meta Ads | Weeks 4 to 12 |
| Ad creatives (static and short video) | 16 | PNG + MP4 | Weeks 3 to 8 |
| Launch email sequence | 4 emails | Email platform | Week 5 |
| Weekly performance report | 9 | Dashboard + email | Every Monday from week 4 |
| Final campaign report and recommendations | 1 | PDF + call | Week 12 |

# 3. Timeline

| Phase | Weeks | Milestone |
| --- | --- | --- |
| 1. Strategy and media plan | Weeks 1 to 2 | Plan approved |
| 2. Creative, landing page and tracking setup | Weeks 3 to 4 | Campaign ready to launch |
| 3. Launch and optimisation | Weeks 4 to 11 | Weekly reports |
| 4. Wrap-up and final report | Week 12 | Final report delivered |

# 4. Client Responsibilities

•  Give admin access to Google Ads, Meta Ads, analytics and the email platform by week 1.

•  Supply product photos, offers and stock levels by week 2.

•  Approve creatives and the landing page within 3 business days.

# 5. Ad Spend

Ad spend of up to USD 15,000 over the campaign is paid by the client directly to Google and Meta. Spend is not part of the agency fee, and changes to the budget are agreed in writing.

# 6. Revisions

Each creative batch and the landing page include 2 rounds of revisions. New ad concepts after launch count as change requests.

# 7. Out of Scope

•  Ad spend

•  Product photography and video shoots

•  Influencer partnerships

•  SEO beyond the landing page, and website changes outside it

# 8. Acceptance Criteria

Strategy, creatives and the landing page are accepted when the client approves them in writing or does not request changes within 3 business days. Tracking is accepted when test orders show in analytics.

# 9. Fees and Payment Schedule

The agency fee is USD 12,600 for the 12-week campaign, paid as follows:

| Payment | Due | Amount |
| --- | --- | --- |
| 1. On signing (40%) | 11/02/2026 | 5,040.00 |
| 2. At launch (30%) | End of week 4 | 3,780.00 |
| 3. On final report (30%) | End of week 12 | 3,780.00 |

Total agency fee  USD 12,600.00

Invoices are due within 14 days. Ad spend is billed separately by Google and Meta to the client.

# 10. Change Requests

Any work outside this scope is requested in writing. The agency replies within 2 business days with the effect on fee and timeline, and the change starts only once both parties approve it in writing.

# Sign-Off

By signing below, both parties agree to this scope of work. It forms part of the service agreement between them.

| FOR THE AGENCY Name: ______________________________ Title: ______________________________ Signature: ______________________________ Date: ______________________________ | FOR THE CLIENT Name: ______________________________ Title: ______________________________ Signature: ______________________________ Date: ______________________________ |
| --- | --- |