| SOCIAL MEDIA MANAGEMENT SCOPE OF WORK Brightline Studio LLC 214 Market Street, Suite 5, Austin, TX 78701, USA hello@brightline.example · +1 (512) 555-0142 Sample scope of work · dates in MM/DD/YYYY | SOW No.: SOW-2026-022 Date: 10/20/2026 Start date: 11/02/2026 |
| --- | --- |

| AGENCY Brightline Studio LLC Maya Torres, Managing Director hello@brightline.example Austin, TX, USA | CLIENT GreenLeaf Organics Inc. Daniel Price, Head of Marketing 77 Cedar Lane, Portland, OR 97205, USA daniel@greenleaf.example |
| --- | --- |

This scope of work covers monthly social media management for GreenLeaf Organics on Instagram, Facebook and LinkedIn, starting with a one-time setup.

# 1. Objectives

•  Grow followers and engagement on Instagram and Facebook month over month.

•  Drive link clicks to the online shop from social content.

•  Build LinkedIn as a channel for wholesale buyers.

•  KPIs are tracked and reported; no specific follower or sales numbers are guaranteed.

# 2. Monthly Deliverables

| Deliverable | Qty | Format | Due |
| --- | --- | --- | --- |
| Content calendar for the next month | 1 | Shared sheet | 25th of each month |
| Feed posts (design and captions) | 12 | Image or carousel | Weekly |
| Stories | 8 | Image or short video | Weekly |
| Reels (edited from client footage) | 4 | Vertical video | Weekly |
| Community management, Monday to Friday | Daily | Replies within 24 business hours | Ongoing |
| Paid social management (up to USD 3,000 spend) | 1 program | Meta Ads | Ongoing |
| Performance report | 1 | PDF + 30-minute call | By the 5th business day |

# 3. Timeline

| Phase | Weeks | Milestone |
| --- | --- | --- |
| Setup: audit, profile optimisation, brand voice | Weeks 1 to 2 | Setup approved |
| First content calendar and posts | Weeks 3 to 4 | First month live |
| Monthly cycle: plan, create, publish, report | Every month | Report and review call |

# 4. Client Responsibilities

•  Give admin access to all three accounts and the Meta ad account.

•  Supply product photos, raw footage and launch dates by the 15th of each month.

•  Approve each content calendar within 3 business days.

# 5. Revisions

Each monthly calendar includes 1 round of revisions. Changes after approval, or posts added mid-month, count toward the next month's allowance or are billed at USD 85 per hour.

# 6. Out of Scope

•  Ad spend, which the client pays directly to Meta

•  Influencer outreach and partnerships

•  Video or photo shoots

•  Crisis PR and paid media on other platforms

# 7. Acceptance Criteria

A month's content is accepted when the client approves the calendar. The monthly report is accepted on delivery unless the client raises a factual error within 5 business days.

# 8. Fees and Payment Schedule

A monthly retainer of USD 2,400, billed in advance, plus a one-time setup fee of USD 900. Minimum term 3 months, then month to month with 30 days' notice.

| Payment | Due | Amount |
| --- | --- | --- |
| Setup fee | On signing | 900.00 |
| Month 1 retainer | 11/02/2026 | 2,400.00 |
| Month 2 retainer | 12/01/2026 | 2,400.00 |
| Month 3 retainer | 01/01/2027 | 2,400.00 |

First quarter total  USD 8,100.00

Invoices are due within 7 days. Ad spend is billed separately by Meta to the client.

# 9. Change Requests

Any work outside this scope is requested in writing. The agency replies within 2 business days with the effect on fee and timeline, and the change starts only once both parties approve it in writing.

# Sign-Off

By signing below, both parties agree to this scope of work. It forms part of the service agreement between them.

| FOR THE AGENCY Name: ______________________________ Title: ______________________________ Signature: ______________________________ Date: ______________________________ | FOR THE CLIENT Name: ______________________________ Title: ______________________________ Signature: ______________________________ Date: ______________________________ |
| --- | --- |