| WEBSITE SCOPE OF WORK Brightline Studio LLC 214 Market Street, Suite 5, Austin, TX 78701, USA hello@brightline.example · +1 (512) 555-0142 Sample scope of work · dates in MM/DD/YYYY | SOW No.: SOW-2026-023 Date: 10/20/2026 Start date: 11/02/2026 |
| --- | --- |

| AGENCY Brightline Studio LLC Maya Torres, Managing Director hello@brightline.example Austin, TX, USA | CLIENT Kavya Home Decor Kavya Rao, Founder 88 Park Avenue, Pune, India kavya@kavyahome.example |
| --- | --- |

This scope of work covers the redesign and rebuild of the Kavya Home Decor website on WordPress, delivered over 10 weeks.

# 1. Objectives

•  A faster, mobile-first site that makes products easy to find.

•  Move existing content to the new site without losing pages.

•  Basic on-page SEO and analytics in place at launch.

# 2. Deliverables

| Deliverable | Qty | Format | Due |
| --- | --- | --- | --- |
| Sitemap and wireframes for key pages | 1 | PDF + Figma | Week 2 |
| Page template designs, 2 design rounds | 12 | Figma | Week 5 |
| WordPress theme development | 12 templates | Staging site | Week 8 |
| Content migration | Up to 40 pages | WordPress | Week 8 |
| On-page SEO basics and GA4 setup | 1 | Live site | Week 9 |
| Browser and device testing | 1 test matrix | Report | Week 9 |
| Launch, training and 30-day support | 1 | Live site + video | Week 10 |

# 3. Timeline

| Phase | Weeks | Milestone |
| --- | --- | --- |
| 1. Discovery, sitemap and wireframes | Weeks 1 to 2 | Wireframes approved |
| 2. Design of 12 page templates | Weeks 3 to 5 | Designs approved |
| 3. Development and content migration | Weeks 6 to 8 | Staging site ready |
| 4. SEO setup and testing | Week 9 | Test report signed off |
| 5. Launch and training | Week 10 | Site live |

# 4. Client Responsibilities

•  Supply final copy and product photos by the end of week 4.

•  Provide hosting, domain and WordPress admin access by week 6.

•  Review each milestone within 3 business days.

# 5. Revisions

Page designs include 2 revision rounds. Development includes fixes for anything that does not match the approved designs. New features after design approval are change requests.

# 6. Out of Scope

•  Copywriting and product photography

•  Hosting and domain fees

•  Paid plugins and themes (billed at cost if needed)

•  Support after the 30-day period

# 7. Acceptance Criteria

•  Key templates score 85 or more for mobile performance in Lighthouse.

•  Key templates are checked against WCAG 2.1 AA.

•  The site works in the latest Chrome, Safari, Firefox and Edge, and on iOS and Android phones in the test matrix.

# 8. Fees and Payment Schedule

The total fee is USD 14,500, paid as follows:

| Payment | Due | Amount |
| --- | --- | --- |
| 1. On signing (30%) | 11/02/2026 | 4,350.00 |
| 2. On design approval (40%) | End of week 5 | 5,800.00 |
| 3. On launch (30%) | End of week 10 | 4,350.00 |

Total  USD 14,500.00

Invoices are due within 14 days. The 30-day support period covers bug fixes, not new features.

# 9. Change Requests

Any work outside this scope is requested in writing. The agency replies within 2 business days with the effect on fee and timeline, and the change starts only once both parties approve it in writing.

# Sign-Off

By signing below, both parties agree to this scope of work. It forms part of the service agreement between them.

| FOR THE AGENCY Name: ______________________________ Title: ______________________________ Signature: ______________________________ Date: ______________________________ | FOR THE CLIENT Name: ______________________________ Title: ______________________________ Signature: ______________________________ Date: ______________________________ |
| --- | --- |